## Feuille1
Partie	Page	Tâche	Estimation (h)	Temps passé (h)	Temps restant (h)
IONIC	EntryPoint	- module entry point -> user input phone number -> get user id -> save id into the storage	1 hr		0
IONIC	routeAuthGard	- all routes should have authguard -> check if user_id is set or not	30 mn		0
IONIC		- create the URL development variables	5 mn		1
IONIC		- mobile money service (deposit, withdraw, transfer)	30 mn		0
IONIC		- credit service (buy, tranfser)	30 mn		0
IONIC		- appel service (call)	15 mn		0
IONIC		- message service (send)	15 mn		0
IONIC		- internet service (navigate)	15 mn		0
IONIC	firebase notification	- config notification on app component -> when receiving new notif then just display an alert	1 hr		2
spring	firebase notification	- create table users_fcm_ids -> when mobile user register to firebase, save the ID of firebase to the database	1 hr		2
spring	firebase notification	- when user sends a new message -> send a request to firebase -> firebase sends notification to user	1 hr		1
IONIC		- offer module (buy_offer, list_offers)	30 mn		0
spring		- consumption management	2 hr		0
angular		- environment variables URL			10 mn
spring		- request mapping to controllers	5 mn		0
spring		- date format for IONIC and modify CDate class	5 mn		10 mn
		- add column isValidated in table Deposit			0
		Automatic phone number generation			0
		Column in customer table phoenumber should be only the number of the customer without +26133			0
		What about the usage of preparedstatement in FctGen			0
		Quand effectuer transaction MVOLA alors entrer mot de passe			0
		HASH PASSWORD			0
		SETUP JWT in spring boot			0
		create a web service for withdraw: simulation of JWT			0
		make web services work in spring boot (deposit, credit)			0
		appel, message, internet			0
		setup notification with firebase			1 hr
		create message navigation in ionic			1 hr
		notification when deposit, withdraw			1 hr
		change prefix to requestmapping in SPRING			0
		isvalidated in table deposit => change all balance request of user			0
		- Base de données: - firebase_cloud_messaging: customer_id, app_id - JWT table:			1hr
		- Interface simulation: appel et internet - Interface pour se connecter - Notification firebase: - Interface espace client pour connaître solde crédit et solde mobile money (which should be firebase notification) - Interface liste des messages			0
		- JWT with spring boot			0
		- Working SPRING BOOT web services			0
		- deploying to heroku			30 mn
		statistiques			1 hr
		nouvelle insertion tarification			0
		solde crédit, solde mobile money			0
		- automatic phone_number generation			0
		- clean up code: controllers should be short			30 mn
		- deploy angular back office to heroku			30 mn
		- maquette			30 mn
		- add specific link to access back office			0
		- add specific link to access front office			0
		- create a operator table (id, name, phone_prefix)			15 mn
		- create a function to get prefix from a phone_number (033/+26133): get prefix from base and compare to check if a number is interior or exterior
		- SQL data types performance
		- when getting input in Offer, if appel is in minutes or hours, transform it into seconds
		- buy offer from credit
		use internet
		find the routes that need to be protected
		implement authentification
		in CDATE class, make dateformat as "yyyy-MM-dd hh:mm"			0
		URL string for mongodb
		- purchase offer credit			0
		- offer appel
		- jwt authentification			0
		- offer algorithm for message and calls with interior and exterior price

		- Exterior phone number when message, call, internet
		- statistics
		- optimisation table SQL
		- buy offer from mobile money
		- remaining offer of a customer			0
		- add code to offer
		- creating offers should be in the admincontroller
		- add endponit to save the token of the registered user
		- function to send a notification, sendNotif(app_token)
		- in find all valid purchases, add a field to offer class: isOneDay, if isOndeDay is true then set the end date of the purchase to be the same day but at 23:59
		- test offre rojo
		- add code to offer
		test isoneday
		- test insertion offer buyinglimit
		- test Enddate of offer
		- test taperina crédit
IONIC		- dépôt, retrait, transfer